## Sheet1
Story Point | User Story Number | Story Risk | Story Description
1
2
3
5
8
13

## Sheet2
Story Point Summary | Story ID | Risk | Done by Midpoint? | Story Description
1 | US 01.02.01 |  | Yes | As an owner, I want to view an item and its details.
| US 02.01.01 |  | Yes | As an owner, I want to see a list of my items.
2
| US 01.01.01 |  | Yes | As an owner, I want to add an item to my items, with a date of purchase or acquisition, brief description, make, model, serial number (if applicable), estimated value, and comment.
| US 01.02.01 |  | Yes | As an owner, I want to view an item and its details.
| US 01.03.01 |  | Yes | As an owner, I want to edit the details of an item
| US 01.04.01 |  | Yes | As an owner, I want to delete an item.
3
| US 02.02.01 |  | Yes? | As an owner, I want to see the total estimated value of the shown items in the list of items.
| US 03.01.01 |  | Yes | As an owner, I want to define tags that can be used to categorize items.
| US 06.01.01 |  | No | As a user, I want a profile with a unique username.
5
| US 02.03.01 |  | Yes | As an owner, I want to select items from the list of items and delete the selected items.
| US 02.05.01 |  |  | As an owner, I want to filter the list of items by date range.
| US 03.02.01 |  |  | As an owner, I want to specify one or more tags for an item.
8
| US 02.04.01 |  |  | As an owner, I want to sort the list of items by date, description, make, or estimated value by ascending or descending order.
| US 02.06.01 |  |  | As an owner, I want to filter the list of items by description keywords.
| US 02.07.01 |  |  | As an owner, I want to filter the list of items by make.
| US 03.03.01 |  |  | As an owner, I want to select items from the list of items and apply one or more tags to the selected items.
| US 03.04.01 |  |  | As an owner, I want to sort the list of items by tags.
| US 03.05.01 |  |  | As an owner, I want to filter the list of items by tags.
13
| US 04.01.01 |  | No | As an owner, I want to take photos using the camera from the app, and attach one or more photographs to an item of mine.
| US 04.02.01 |  | No | As an owner, I want to use photos from my photo gallery, and attach one or more photographs to an item of mine
| US 04.03.01 |  | No | As an owner, I want to delete an attached photograph for an item of mine.
| US 05.01.01 |  | No | As an owner, I want help to specify the serial number for an item by automatically identifying the number from an image taken by the camera.
21
| US 05.02.01 |  | No | As an owner, I want help to specify the description for an item by automatically identifying the product barcode from an image taken by the camera and using associated product information.